## Sheet1
Quarter | Goals | Start Date | Due Date | Status | Note
Q1 | Complete Udacity Course | 2024-01-05 | 2024-03-31 | Done
Q2 | Design architecture for current project | 2024-04-01 | 2024-06-30 | In Progress
Q3 | Apply automation test to current project | 2024-07-01 | 2024-09-30 | TBD | use playwright framework
Q4 | Documentation, release note, security scan code, release candidate | 2024-10-01 | 2024-12-31 | TBD
Goals |  | Estimation (days) | Complete Day
Q1 | Start learning udacity course | 20 | 2024-01-25
| do Exercise | 20 | 2024-02-14
| Resolve conflict dependencies | 16 | 2024-03-01
| implement project | 30 | 2024-03-31
Q2 | Investigate system | 30 | 2024-05-01
| clarify requirement from stakeholders | 30 | 2024-05-31
| Review stacks and starting design architecture | 30 | 2024-06-30
Q3 | Research automation test (playwright framework) | 15 | 2024-07-16
| Apply automation test | 35 | 2024-08-20
| Integrate with azure pipeline | 15 | 2024-09-04
| Apply best practice | 26 | 2024-09-30
Q4 | Documentation project | 35 | 2024-11-05
| Write release note for RC version | 15 | 2024-11-20
| apply security scan code before release | 35 | 2024-12-25
Formulas:
Due Date = C2+[Start Date]
Due Date = [Due Date, row above]+[Start Date]